LIBERTARIAN PARTY BALLOT ACCESS ACTION REPORT

Libertarian National Committee meeting

New Orleans, Louisiana

December 13-14, 2014

Dear Colleagues:

If we lived in a nation with just election laws, we wouldn’t have to pursue ballot access.  Unfortunately, that is not the case.  The following memo addresses petitioning opportunities for the LNC in 2015 and 2016.

I want to thank Richard Winger and Bob Johnston, LP of Maryland Chair and an Independent Contractor to the LNC, for their assistance in updating this report.

We currently have ballot access for our 2016 Presidential ticket in the following 30 states:  AK, AZ, CA, CO, DE, FL, GA, HI, ID, IN, KS, LA, MD, MI, MS, MO, MT, NE, NV, NM, NC, ND, OR, SC, TX, UT, VT, WV, WI & WY.

I will now address the other 20 states and DC:

AL:  The LP can start a party petition anytime (39,975 valid sigs), but I presume that we will do an Independent petition for 5,000 valid sigs in 2016 after the Presidential nomination.  I budget $15,000.

AR:  I have not yet been in contact with the LPAR regarding their desires, but I presume that the LPAR will want to do a party petition for 10,000 valid sigs that we could do in 2015.  I budget $30,000.

CT:  7,500 valid sigs in 2016 for President.  The LPCT is working with the ACLU to possibly litigate the out-of-state petitioner ban in CT.  This drive will likely need some subsidization from the LNC.  I budget $25,000.

DC:  I estimate a 4,600 valid sig petition drive for President in 2016.  I budget $15,000 from the LNC.

IL:  25,000 valid sig petition drive for President & US Senate in 2016.  I will budget $66,500, which was the budgeted amount for 2014.

IA:  1,500 valid sig petition drive for President.  This required subsidization in 2012 from the LNC.  Hopefully not in 2016.

KY:  5,000 valid sig petition drive for President can start the day after Election Day 2016.  I budget $7,500 in 2015 and $7,500 in 2016.

ME:  The LPME is working with Scott Kohlhaas in a voter registration drive.  The LPME needs 5,000 registered voters to become an officially recognized political party in Maine, which would give the LPME ballot access.  This registration drive cannot start until December 2014.  It will have to conclude by December 2015.  Scott Kohlhaas anticipates this registration drive will succeed.  I am not planning on any LNC subsidization at this time.

MA:  We will need to do a 10,000 valid sig petition drive for President after Memorial Day 2016, unless we receive permission from the Secretary of State to list only our Presidential electors.  If we got that permission, the petition drive could start in February 2016.  Deadline:  August 1, 2016.

Please note that if we had party status in MA, we would not have to petition at all to get our Presidential ticket on the ballot there.

MN:  A 2,000 valid sig petition drive for President after the Memorial Day 2016 weekend convention.  I will plan on this being done by the LPMN.

NH:  1,500 valid sigs in each of two congressional districts (3,000 valid sigs total).  I have not seen anything out of the LPNH recently that would indicate that it could handle this petition drive on its own.  I budget $15,000 in 2016.

NJ:  800 valid sigs after Memorial Day 2016.  Although the LNC needed to subsidize in 2012, I would hope they could do this on their own in 2016.

NY:  We will need 15,000 valid sigs for our Presidential ticket in 2016.  I budget $30,000 from the LNC.

OH:  The LPOH is still in court regarding Ohio’s ballot access laws.  We should see how this litigation plays out before considering what to do with Ohio for 2016.

OK:  A party petition would be 41,242 valid sigs.  A presidential petition would be 40,047 valid sigs.  The cost to do an LPOK petition drive would likely be about $125,000.  NOTE:  This dollar amount is not included in the 2015 & 2016 summaries below.

PA:  We are looking at probably about a 25,000 valid sig petition drive in PA starting in February 2016.  We are probably looking at an expenditure of $70,000.

RI:  A 1,000 valid sig petition drive.  I don’t think the LPRI can do this themselves.  We are probably looking at an LNC expenditure of $2,500.

SD:  The LP will lose its party status in SD in November, because the LPSD did not run someone for Governor this year.  However, the LPSD has a new Chairman, Emmett Reistroffer, who seems to have a great desire to move the LPSD forward.  A party petition for 6,936 valid sigs would get us two elections (2016 & 2018), with a possibility of retaining ballot status if we get 2.5% for Governor in 2018.  I budget $20,000 of LNC funds in 2015.

TN:  275 valid sig petition drive for President in 2016.  The LPTN should handle this itself.  The LPTN needs to work to get this done well ahead of the deadline in 2016, not let it go to a last day fire drill, as in 2012.

VA:  5,000 valid sig petition drive for President in 2016.  The LPVA should handle this itself.

WA:  1,000 valid sig petition drive for President in 2016.  The LPWA should handle this itself.

2015 Summary:

AR $30,000

KY $7,500

SD $20,000

Total:  $57,500

2016 Summary:

AL $15,000

CT $25,000

DC $15,000

IL $66,500

KY $7,500

MA $25,000

NH $15,000

NY $30,000

PA $70,000

RI $2,500

Total:  $271,500

BALLOT ACCESS LOBBYING

From an email from Richard Winger to me:  “We can reasonably expect bills to be introduced in AL, AR, CT, OH, OK, PA, SD & TN.  And, with encouragement from the national office, we could get bills in a lot more states.  The Greens are working on this in some states; it doesn’t have to be all just our work.”

I think there needs to be greater involvement by a National Office employee, presumably the Political Director, in helping our state parties with ballot access lobbying.